## General Flow
1 | Business Requirement
↓
2 | Customer' Requirements
↓
3 | Candidate Selection
↓
4 | Initial 'Customer' Application
↓
5 | Qualification Verification
• Experience
• AML
• A350 Type Training
• HAECO Authorization
(A359_TXWB_B1 / A359_TXWB_B2STAR)
↓
6 | Supporting Document Submission
↓
7 | Customer' QA Review
↓
8 | Customer' Training Plan
↓
9 | Training Record
↓
10 | Customer' Training Verification
↓
11 | Customer' CS Roster
↓
12 | Customer' Authorization Effective

## KE
Step No. | Main Step | Sub-Step | Status | Actions | Owner | PIC | Documents Source | Target Completion Date | Ref Duration
1 | Business Requirement | Business Requirement Raised | ✅ Complete | Receive customer operational request and confirm operational support requirement | HX Account | Irene | KE A350 Operational Request | 2026-08-11 | N/A
2 | Business Requirement | KE Qualification Requirements Received | ✅ Complete | Obtain authorization requirements, qualification criteria and submission requirements from KE | HX LMOC | SH | KE QA / Training Email | 2026-08-13 | ~7 Days
3 | Candidate Qualification | LMS Authorization Profile Verified | ✅ Complete | Verify applicable KE authorization profiles are available in LMS | HX QA | Josephine | LMS Authorization Profiles | Pre-existing | ~60 Days
4 | Candidate Qualification | Candidate Selection | ✅ Complete | Review available A350 certifiers and identify eligible candidates against KE qualification requirements | HX LMOC | Christine | LM Candidate Review | 2026-08-27 | ~14 Days
5 | Candidate Qualification | Initial KE Application Submission | ✅ Complete | Complete and submit KE CS Application Forms for candidate qualification assessment | HX LMOC | SH | KE CS Application Form | 2026-09-09 | ~7 Days
6 | Candidate Qualification | Experience Qualification Verification | ✅ Complete | Verify maintenance experience requirements and obtain management certification letter | HX LM Manager | Christine | Experience Certification Letter | 2026-09-10 | ~3 Days
7 | Candidate Qualification | AML Qualification Verification | ✅ Complete | Submit HKAML licence copies and complete KE QA AML review | HX LMOC | SH | HKAML Licence Copies | 2026-09-11 | ~2 Days
8 | Candidate Qualification | A350 Type Training Verification | ✅ Complete | Verify A350 training qualifications and supporting training records for KE QA review | HX Training | Training Team | LMS Training Records / Type Rating Records | 2026-09-14 | ~14 Days
9 | Candidate Qualification | HAECO Authorization Verification | ✅ Complete | Verify HAECO authorization status and provide company authorization evidence requested by KE QA | HX QA | Josephine | HAECO Authorization Records | 2026-09-14 | ~7 Days
10 | Application Package | Supporting Document Submission | ✅ Complete | Submit AML, Training Records, Company Authorization and Experience Certification documents to KE QA | HX LMOC | SH | Consolidated Submission Package | 2026-09-14 | ~3 Days
11 | Application Package | KE QA Qualification Review | ✅ Complete | KE QA completed qualification review and confirmed applicants satisfy KE CS requirements | KE QA | Lee Geonhyung / Kim Jaehyeok | KE QA Qualification Review | 2026-09-14 | ~10 Days
12 | KE Training | KE FTH Training Release | ✅ Complete | KE Training issued FTH syllabus, training materials and CAR requirements | KE Training | Jintae Kim | FTH Package / CAR Form | 2026-09-14 | ~14 Days
13 | KE Training | Training Arrangement | 🔄 In Progress | Coordinate trainees, training schedule, DST support and self-study arrangements | HX LMOC | SH | MOD1 / MOD2 Package | 2026-09-30 | ~14 Days
14 | KE Training | MOD1 Procedure Training | ❌ Not Started | Complete LMM, EDTO, RVSM & CAT II/III procedure training for applicable new applicants | HX Certifiers | DST | MOD1 Training Material | 2026-10-31 | ~30 Days
15 | KE Training | MOD2 A350 TR / PRPO Training | ❌ Not Started | Complete A350 TR & PRPO self-study / Read & Sign training | HX Certifiers | Certifiers | A350 TR & PRPO Guide | 2026-10-31 | ~30 Days
16 | KE Training | Training Completion Evidence Collection | ❌ Not Started | Collect attendance evidence, trainee signatures and training completion records | HX LMOC | SH | Training Records | 2026-11-07 | ~7 Days
17 | CAR Process | FTH CAR Preparation | ❌ Not Started | Complete CAR forms including trainee details, dates, authorization numbers and instructor verification | HX LMOC | SH | CAR Form R10 | 2026-11-14 | ~7 Days
18 | CAR Process | FTH CAR Submission | ❌ Not Started | Submit completed CAR package to KE Training for verification | HX LMOC | SH | Completed CAR Package | 2026-11-21 | ~5 Days
19 | CAR Process | KE Training Verification | ❌ Not Started | KE Training reviews CAR and confirms satisfactory training completion | KE Training | Jintae Kim | CAR Verification | 2026-12-05 | ~14 Days
20 | Authorization | Final KE QA Approval | ❌ Not Started | Submit training verification result and close remaining QA comments | KE QA | Kim Jaehyeok | KE Training Confirmation | 2026-12-18 | ~14 Days
21 | Authorization | KE CS Roster Issuance | ❌ Not Started | KE QA issues revised CS Roster for approved personnel | KE QA | Kim Jaehyeok | Revised KE CS Roster | 2027-01-08 | ~14 Days
22 | Authorization | Authorization Effective | ❌ Not Started | Distribute roster and update HAECO internal authorization tracking records | HX QA | Josephine | KE CS Roster | 2027-01-08 | 1 Day
~7 Months
1. C/S application form (Step 5)
2. National license copies (Step 7)
3. Training transcript or certificate of the A/C type (Step 8)
4. Company authorization (Step 9)
5. Confirmation of experience in case new applicant (Step 6)
Lessons Learned from Previous
The previous project encountered repeated delays caused by:
1 | Incorrect CAR Forms
2 | Wrong Employee Numbers
3 | Wrong KE Authorization Numbers
4 | Missing Experience Certificate
5 | Missing Training Records
6 | Re-signing of CAR after corrections
7 | Multiple QA clarification rounds
Pre-Submission Checklist
✅ Employee Number
✅ KE Auth Number (if applicable)
✅ AML Copy
✅ A350 Type Training Certificate / Transcript
✅ Experience Certificate
✅ Company Authorization
✅ Candidate Name Consistency
✅ Correct CAR Form Version
✅ Required Signatures Completed
Note on C6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1. C/S application form (Step 5)
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5. Confirmation of experience in case new applicant (Step 6)
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2. National license copies (Step 7)
Note on C9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3. Training transcript or certificate of the A/C type (Step 8)
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4. Company authorization (Step 9)
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Package of Steps 6-9 submitted to KE QA
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KE reviews all above documents
Note on C15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: *DST : HKG-013/029/078

## Sheet1
1. C/S application form (Step 5) 2. National license copies (Step 7) 3. Training transcript or certificate of the A/C type (Step 8) 4. Company authorization (Step 9) 5. Confirmation of experience in case new applicant (Step 6)
Step No. | Main Step | Sub-Step | Status | Actions | Owner | PIC | Documents Source | Target Completion Date | Ref Duration
1 | Business Requirement | Business Requirement Raised | ✅ Complete | Receive customer operational request and confirm operational support requirement | HX Account | Irene | KE A350 Operational Request | 2026-08-11 | N/A
2 | Business Requirement | KE Qualification Requirements Received | ✅ Complete | Obtain authorization requirements, qualification criteria and submission requirements from KE | HX LMOC | SH | KE QA / Training Email | 2026-08-13 | ~7 Days
3 | Candidate Qualification | LMS Authorization Profile Verified | ✅ Complete | Verify applicable KE authorization profiles are available in LMS | HX QA | Josephine | LMS Authorization Profiles | Pre-existing | ~60 Days
4 | Candidate Qualification | Candidate Selection | ✅ Complete | Review available A350 certifiers and identify eligible candidates against KE qualification requirements | HX LMOC | Christine | LM Candidate Review | 2026-08-27 | ~14 Days
5 | Candidate Qualification | Initial KE Application Submission | ✅ Complete | Complete and submit KE CS Application Forms for candidate qualification assessment | HX LMOC | SH | KE CS Application Form | 2026-09-09 | ~7 Days
6 | Candidate Qualification | Experience Qualification Verification | ✅ Complete | Verify maintenance experience requirements and obtain management certification letter | HX LM Manager | Christine | Experience Certification Letter | 2026-09-10 | ~3 Days
7 | Candidate Qualification | AML Qualification Verification | ✅ Complete | Submit HKAML licence copies and complete KE QA AML review | HX LMOC | SH | HKAML Licence Copies | 2026-09-11 | ~2 Days
8 | Candidate Qualification | A350 Type Training Verification | ✅ Complete | Verify A350 training qualifications and supporting training records for KE QA review | HX Training | Training Team | LMS Training Records / Type Rating Records | 2026-09-14 | ~14 Days
9 | Candidate Qualification | HAECO Authorization Verification | ✅ Complete | Verify HAECO authorization status and provide company authorization evidence requested by KE QA | HX QA | Josephine | HAECO Authorization Records | 2026-09-14 | ~7 Days
10 | Application Package | Supporting Document Submission | ✅ Complete | Submit AML, Training Records, Company Authorization and Experience Certification documents to KE QA | HX LMOC | SH | Consolidated Submission Package | 2026-09-14 | ~3 Days
11 | Application Package | KE QA Qualification Review | ✅ Complete | KE QA completed qualification review and confirmed applicants satisfy KE CS requirements | KE QA | Lee Geonhyung / Kim Jaehyeok | KE QA Qualification Review | 2026-09-14 | ~10 Days
12 | KE Training | KE FTH Training Release | ✅ Complete | KE Training issued FTH syllabus, training materials and CAR requirements | KE Training | Jintae Kim | FTH Package / CAR Form | 2026-09-14 | ~14 Days
13 | KE Training | Training Arrangement | 🔄 In Progress | Coordinate trainees, training schedule, DST support and self-study arrangements | HX LMOC | SH | MOD1 / MOD2 Package | 2026-09-30 | ~14 Days
14 | KE Training | MOD1 Procedure Training | ❌ Not Started | Complete LMM, EDTO, RVSM & CAT II/III procedure training for applicable new applicants | HX Certifiers | DST | MOD1 Training Material | 2026-10-31 | ~30 Days
15 | KE Training | MOD2 A350 TR / PRPO Training | ❌ Not Started | Complete A350 TR & PRPO self-study / Read & Sign training | HX Certifiers | Certifiers | A350 TR & PRPO Guide | 2026-10-31 | ~30 Days
16 | KE Training | Training Completion Evidence Collection | ❌ Not Started | Collect attendance evidence, trainee signatures and training completion records | HX LMOC | SH | Training Records | 2026-11-07 | ~7 Days
17 | CAR Process | FTH CAR Preparation | ❌ Not Started | Complete CAR forms including trainee details, dates, authorization numbers and instructor verification | HX LMOC | SH | CAR Form R10 | 2026-11-14 | ~7 Days
18 | CAR Process | FTH CAR Submission | ❌ Not Started | Submit completed CAR package to KE Training for verification | HX LMOC | SH | Completed CAR Package | 2026-11-21 | ~5 Days
19 | CAR Process | KE Training Verification | ❌ Not Started | KE Training reviews CAR and confirms satisfactory training completion | KE Training | Jintae Kim | CAR Verification | 2026-12-05 | ~14 Days
20 | Authorization | Final KE QA Approval | ❌ Not Started | Submit training verification result and close remaining QA comments | KE QA | Kim Jaehyeok | KE Training Confirmation | 2026-12-18 | ~14 Days
21 | Authorization | KE CS Roster Issuance | ❌ Not Started | KE QA issues revised CS Roster for approved personnel | KE QA | Kim Jaehyeok | Revised KE CS Roster | 2027-01-08 | ~14 Days
22 | Authorization | Authorization Effective | ❌ Not Started | Distribute roster and update HAECO internal authorization tracking records | HX QA | Josephine | KE CS Roster | 2027-01-08 | 1 Day